## Transactions
Project Full Name | Transaction Type | Expense Date | Description | Quantity | Gross | Item | Tran Type | Task | Comments | Approval Status | Project Number | Transaction Number | Expense Account Name | Expense Account Number
0

## Account Overview
Transaction Report: TEMPLATE
|  | Client: |  |  |  | Project Manager:
|  | WMJ Code: |  |  |  | Date: | 2026-05-04
Billable Projects
WMJ Code + Name | Period of Performance | Total Labor Award | Incurred Labor Period of Performance | Incurred Labor Project To Date | Remaining Labor | % Labor Utilized (automated) | % Earned Value (manual) | Remaining Work / Flags
[5 empty] | 0 | #DIV/0! | 0%
[5 empty] | 0 | #DIV/0! | 0%
[5 empty] | 0 | #DIV/0! | 0%
[5 empty] | 0 | #DIV/0! | 0%
[5 empty] | 0 | #DIV/0! | 0%
TOTAL |  | 0 | 0 |  | 0 | #DIV/0! | #DIV/0!
Non-Billable Work | [5 empty] | Total Account Spend
Project Name & Code | Incurred Labor | Remaining Work & Flags |  |  |  | 0

## Weekly Project Spend
Weekly Project Spend
Client: |  | 0 |  | Project Manager: | 0
WMJ Code: |  | 0 |  | Date: | 2026-05-04
Project 1 |  |  |  | Project 1
Start | 2026-01-02 | Labor Funds Utilized | 0 | Phase | Estimated Cost | Actual Cost | Remaining Funds | Earned Value
End | 2026-03-19 | Completed Weeks | 17.4286 | Setup |  |  | 0 | 0%
Today | 2026-05-04 | Weekly Average | 0 | Discovery |  |  | 0 | 0%
|  | Labor Funds Remaining | 0 | Strategy |  |  | 0 | 0%
|  | Weeks Remaining | #NUM! | Content Hub |  |  | 0 | 0%
|  | Weekly Average | #NUM! | Creative Concepts |  |  | 0 | 0%
|  |  |  | Creative Execution |  |  | 0 | 0%
|  |  |  | Deploy + Ongoing Mngt |  |  | 0 | 0%
|  |  |  | Total | 0 | 0 | 0 | 0%
Project 2 |  |  |  | Project 2
Start | 2026-01-02 | Labor Funds Utilized | 0 | Phase | Estimated Cost | Actual Cost | Remaining Funds | Earned Value
End | 2026-03-19 | Completed Weeks | 17.4286 | Setup |  |  | 0 | 0%
Today | 2026-05-04 | Weekly Average | 0 | Discovery |  |  | 0 | 0%
|  | Labor Funds Remaining | 0 | Strategy |  |  | 0 | 0%
|  | Weeks Remaining | #NUM! | Content Hub |  |  | 0 | 0%
|  | Weekly Average | #NUM! | Creative Concepts |  |  | 0 | 0%
|  |  |  | Creative Execution |  |  | 0 | 0%
|  |  |  | Deploy + Ongoing Mngt |  |  | 0 | 0%
|  |  |  | Total | 0 | 0 | 0 | #DIV/0!
Project 3 |  |  |  | Project 3
Start | 2025-06-10 | Labor Funds Utilized | 0 | Phase | Estimated Cost | Actual Cost | Remaining Funds | Earned Value
End | 2026-03-25 | Completed Weeks | 46.8571 | Setup |  |  | 0 | 0%
Today | 2026-05-04 | Weekly Average | 0 | Discovery |  |  | 0 | 0%
|  | Labor Funds Remaining | 0 | Strategy |  |  | 0 | 0%
|  | Weeks Remaining | #NUM! | Content Hub |  |  | 0 | 0%
|  | Weekly Average | #NUM! | Creative Concepts |  |  | 0 | 0%
|  |  |  | Creative Execution |  |  | 0 | 0%
|  |  |  | Deploy + Ongoing Mngt |  |  | 0 | 0%
|  |  |  | Total | 0 | 0 | 0 | 0%

## FRC-0014 Stoplight (hidden)
PROJECT NAME | 20. DT (IRM Pt II) | PROJECT CODE | FRC-0014 | STATUS KEY | BUDGET KEY
PROJECT MANAGER | Maddie | DATE OF STATUS ENTRY | 2026-05-04 | PROGRESS HALTED | OVER
PERIOD COVERED | February 2025 - June 2025 | PROJECTED DATE OF COMPLETION | 2025-06-30 | AT RISK | ON
|  |  |  | HEALTHY | UNDER
PROJECT STATUS THIS WEEK
OVERALL PROJECT STATUS | PROGRESS HALTED | SUMMARY | ON HOLD
PROJECT COMPONENTS
COMPONENT | STATUS | NOTES
BUDGET | ON | We are tracking slightly over budget; We're at 14% of the budget utilized with an estimated 5% of the work completed.
SCHEDULE | PROGRESS HALTED | ON HOLD
QUALITY |  | N/A
SCOPE |  | N/A
RISKS |  | N/A
ROADBLOCKS |  | N/A
UPCOMING WORK
DATE | STATUS | DETAILS
Complete | HEALTHY | Billing Vic delivered final invoice ($4,518.75)
TBD | AT RISK | Campaign KO Laura said we'll have more info on 4/25

## WMJ-0001 Stoplight
Project Stoplight Report
Project Name: |  | Project Manager: | 0
WMJ Code: | 0 | Date: | 2026-05-04
Overall Project Status
Summary | HEALTHY | Overall project summary for the week of reporting goes here
Project Components
Component | Status | Notes |  | Status Key | Budget Key
Budget | UNDER | Details about project budget go here (pull numbers from Account Overview tab) ex. We are tracking under budget with 82% of the budget utilized with an estimated 92% of the work completed. |  | HEALTHY | UNDER
Schedule | AT RISK | Details about project schedule go here. ex. The team has fallen behind schedule, so the internal reviews will need to move quickly. |  | AT RISK | ON
Quality | HEALTHY | Details about project quality go here. ex. We've been delivering high quality work and the client has been impressed. |  | PROGRESS HALTED | OVER
Scope | AT RISK | Details about project scope go here. ex. We were only scoped for 2 rounds of client review and are now on round 3.
Risks | AT RISK | Details about project risks go here. ex. We had scoped to work with x resource, who is now unavailable.
Roadblocks | PROGRESS HALTED | Details about project roadblocks go here. ex. Client is unable to give feedback on x deliverable until their leadership has reviewed.
Upcoming Work
Date | Status | Details
1/2 | HEALTHY | Deliverable 1 Status updates and deliverable details go here.
2/3 | PROGRESS HALTED | Deliverable 2 Status updates and deliverable details go here.
3/4 | HEALTHY | Deliverable 3 Status updates and deliverable details go here.

## WMJ-0002 Stoplight
Project Stoplight Report
Project Name: |  | Project Manager: | 0
WMJ Code: | 0 | Date: | 2026-05-04
Overall Project Status
Summary | AT RISK | Overall project summary for the week of reporting goes here
Project Components
Component | Status | Notes |  | Status Key | Budget Key
Budget | UNDER | Details about project budget go here (pull numbers from Account Overview tab) ex. We are tracking under budget with 82% of the budget utilized with an estimated 92% of the work completed. |  | HEALTHY | UNDER
Schedule | AT RISK | Details about project schedule go here. ex. The team has fallen behind schedule, so the internal reviews will need to move quickly. |  | AT RISK | ON
Quality | HEALTHY | Details about project quality go here. ex. We've been delivering high quality work and the client has been impressed. |  | PROGRESS HALTED | OVER
Scope | AT RISK | Details about project scope go here. ex. We were only scoped for 2 rounds of client review and are now on round 3.
Risks | AT RISK | Details about project risks go here. ex. We had scoped to work with x resource, who is now unavailable.
Roadblocks | PROGRESS HALTED | Details about project roadblocks go here. ex. Client is unable to give feedback on x deliverable until their leadership has reviewed.
Upcoming Work
Date | Status | Details
1/2 | HEALTHY | Deliverable 1 Status updates and deliverable details go here.
2/3 | PROGRESS HALTED | Deliverable 2 Status updates and deliverable details go here.
3/4 | HEALTHY | Deliverable 3 Status updates and deliverable details go here.

## WMJ-0003 Stoplight
Project Stoplight Report
Project Name: |  | Project Manager: | 0
WMJ Code: | 0 | Date: | 2026-05-04
Overall Project Status
Summary | PROGRESS HALTED | Overall project summary for the week of reporting goes here
Project Components
Component | Status | Notes |  | Status Key | Budget Key
Budget | UNDER | Details about project budget go here (pull numbers from Account Overview tab) ex. We are tracking under budget with 82% of the budget utilized with an estimated 92% of the work completed. |  | HEALTHY | UNDER
Schedule | AT RISK | Details about project schedule go here. ex. The team has fallen behind schedule, so the internal reviews will need to move quickly. |  | AT RISK | ON
Quality | HEALTHY | Details about project quality go here. ex. We've been delivering high quality work and the client has been impressed. |  | PROGRESS HALTED | OVER
Scope | AT RISK | Details about project scope go here. ex. We were only scoped for 2 rounds of client review and are now on round 3.
Risks | AT RISK | Details about project risks go here. ex. We had scoped to work with x resource, who is now unavailable.
Roadblocks | PROGRESS HALTED | Details about project roadblocks go here. ex. Client is unable to give feedback on x deliverable until their leadership has reviewed.
Upcoming Work
Date | Status | Details
1/2 | HEALTHY | Deliverable 1 Status updates and deliverable details go here.
2/3 | PROGRESS HALTED | Deliverable 2 Status updates and deliverable details go here.
3/4 | HEALTHY | Deliverable 3 Status updates and deliverable details go here.

## Stoplight Rollup
Account Rollup Stoplight Report
Client: | 0 | Project Manager: | 0
WMJ Code: | 0 | Date: | 2026-05-04
Overall Project Status
Summary | HEALTHY | Overall project summary for the week of reporting goes here
Project Components
Component | Status | Notes |  | Status Key | Budget Key
Budget | UNDER | Details about project budget go here (pull numbers from High-Level tab) ex. We are tracking under budget with 82% of the budget utilized with an estimated 92% of the work completed. |  | HEALTHY | UNDER
Schedule | AT RISK | Details about project schedule go here. ex. The team has fallen behind schedule, so the internal reviews will need to move quickly. |  | AT RISK | ON
Quality | HEALTHY | Details about project quality go here. ex. We've been delivering high quality work and the client has been impressed. |  | PROGRESS HALTED | OVER
Scope | AT RISK | Details about project scope go here. ex. We were only scoped for 2 rounds of client review and are now on round 3.
Risks | AT RISK | Details about project risks go here. ex. We had scoped to work with x resource, who is now unavailable.
Roadblocks | PROGRESS HALTED | Details about project roadblocks go here. ex. Client is unable to give feedback on x deliverable until their leadership has reviewed.
Active Projects
Project Code | Status | Details
WMJ-0001 | HEALTHY | Project 1 High level project status goes here.
WMJ-0002 | AT RISK | Project 2 High level project status goes here.
WMJ-0003 | PROGRESS HALTED | Project 3 High level project status goes here.